## Values
Type the Prescribed Fire Plan name here |  | Quantity | Significance | Values Description: Describe the identified off-site, on-site and political values
Values | On-Site | None | Low
| Off-Site | Multiple | Mod
| Public/Political Interest | Few | High
Note on B2: VALUES INSIDE THE PRESCRIBED FIRE PROJECT AREA (ON-SITE VALUES) Valued resources (human, natural, cultural) located within the project area directly affected by implementation of the prescribed fire.
Note on B3: VALUES OUTSIDE PRESCRIBED FIRE PROJECT AREA (OFF SITE VALUES) Valued resources (human, natural, cultural) located outside the project area that may be affected by implementation of the prescribed fire.
Note on B4: PUBLIC AND POLITICAL INTEREST The degree of public and political interest in the implementation and outcome of the prescribed fire.

## Preliminary Risk
Element | Preliminary Risk | Risk Rating Descriptors | Agency Administrator/Preparer Discussion Completed
Safety | Mod | • Safety issues are pronounced and require detailed briefings, with certain hazards requiring special caution. • A small organization with a single branch results in modest exposure of personnel to hazards. • Adverse impacts to public health and safety are possible. • At least one activity is low frequency/high risk. • Fatigue and extended exposure to hazards are anticipated. | No
Fire Behavior | High | • Major variations in the fuel complex are likely to result in more intense fire behavior variations. • Wide variations in fire behavior may present major control challenges. • Terrain encompasses a wide range in slope steepness, abrupt changes in slope, and several directional aspects that lead to widely variable and unpredictable local winds and microclimate differences. • High intensity fire behavior may be expected outside the unit with high rates of spread, torching, possible crown fire runs. • Probability of ignition outside of the unit is high and short and long range spotting can be expected. • Potential fire spread and behavior outside the unit is equal to or greater than inside the unit. | No
Resistance to Containment | Mod | • Potential for multiple wildfire mechanisms such as spot fires or slopovers that can propagate at moderate rates of spread but can be held by prompt holding actions. • Some fuel concentrations or ladder fuels exist near critical holding points. • Expected fire intensities in the primary fuel type create little potential to challenge standard fire lines. • The probability of ignition in fuels outside of control lines is low to moderate. • Some dependency on natural fuel breaks to hold the prescribed fire. • Local drought and or fire indices are expected to be moderate to high. | No
Ignition Procedures and Methods | Mod | • Multiple firing sequences patterns and timing must be coordinated to meet project objectives and reduce the risk of an unexpected or adverse event. • Specific fire intensities or ROS are somewhat critical for meeting resource objectives but are readily attained by placing local skill sets in firing boss positions. | No
Prescribed Fire Duration | Mod | • Active ignition, fire spread, and patrol is expected to occur for several operational periods. • Some residual burning (heavy fuel smoldering, stump holes, etc.) is expected to occur for several days after the primary burn out of the unit. • Mop-up and patrol is typical with minimal resource and equipment needs. • Primary holding phase is expected to be completed within reasonably predictable local weather forecasts. • The prescribed fire depends on accurate forecasts through three days. | No
Smoke Management | High | • Conspicuous smoke will be produced creating significant public concern. • The possibility of health and safety issues due to smoke exposure exists. • Strong, widespread social/political concern about smoke is common in the affected area. • High possibility for a NAAQS exceedance violation. • Smoke impacts affect several prescribed fire plan elements. | No
Number and Dependence of Activities | Mod | • Several activities depend on achievement of previous or concurrent actions. • Several activities are interactive. • Communication is routine for coordination of activities and project success. • The project involves another land management agency, ownership or jurisdiction but project completion is not dependent on coordinated implementation. • Adjacent ownership supports the implementation of the prescribed fire. | No
Management Organization | Mod | • Two levels of supervision are needed (i.e. Burn Boss, Ignition Specialist, and/or Holding Specialist, plus lighters and holders). • Special skills or supervision required for one function (RXB2 is suggested). | No
Treatment/Resource Objectives | Mod | • Issues are present that hamper or may prevent meeting treatment resource objectives. • Failure to meet objectives could have short-term adverse impacts. • Associated resources could be damaged if the prescribed fire did not meet resource objectives. • Few critical holding points. | No
Constraints | Low | • Constraints exist with little impact on implementing the prescribed fire or achieving objectives. | No
Project Logistics | Mod | • Some phases of the prescribed fire may require logistical support in order to safely meet project objectives. • Limited amount of special equipment or communication equipment requiring more intensive logistical support may be needed to complete the project. | No
Note on A2: SAFETY Hazards to personnel and public from planned prescribed fire activities through all phases of the prescribed fire. Safety is always considered individually for all elements.
Note on A4: FIRE BEHAVIOR The difficulty of achieving the desired range of fire intensity, rate of spread and flame lengths to meet the prescribed fire objectives.
Note on A6: RESISTANCE TO CONTAINMENT: The conditions that influence the potential for a prescribed fire to leave the ignition unit or project area and resist containment effort.
Note on A8: IGNITION PROCEDURES AND METHODS Number and type of ignition devices, patterns, sequencing and/or timing required to safely ignite the prescribed fire and meet the objectives.
Note on A10: PRESCRIBED FIRE DURATION The length of time (hours, days or weeks) that active ignition, fire spread, and primary holding operations (critical holding points are secure, transitioning to mop-up and patrol, etc.) are expected to occur in order to fully implement the prescribed fire.
Note on A12: SMOKE MANAGEMENT The actions implemented by prescribed fire personnel directed at reducing the amount of smoke entering populated areas or impacting sensitive sites. Smoke management includes avoiding significant deterioration of air quality and violations of National Ambient Air Quality Standards, and minimizing or eliminating visibility impacts in Class I areas.
Note on A14: NUMBER AND DEPENDENCE OF ACTIVITIES Number and sequence of activities required to safely implement the prescribed fire and meet objectives through all phases of the project, including logistics, pre and post burn considerations, communication, test fire, ignition and holding operations, contingency actions (if implemented), mop-up and patrol, monitoring, and ensuring firefighter and public safety.
Note on A16: MANAGEMENT ORGANIZATION The organizational capabilities needed to safely achieve objectives specified in the prescribed fire plan. This includes all phases of the prescribed fire until declared out.
Note on A18: TREATMENT/ RESOURCE OBJECTIVES The degree of difficulty to meet specific, measurable, achievable, realistic, time-sensitive treatment and resource objectives for the prescribed fire.
Note on A20: CONSTRAINTS Conditions or requirements that place sideboards on the prescribed fire plan implementation. Example: Seasonal timing, logistical restrictions, smoke management restrictions, and national preparedness levels four, and five.
Note on A22: PROJECT LOGISTICS Facilities, services and supplies required to support all phases of the prescribed fire (includes access complexity).

## Post-Plan Risk
Element | Preliminary Risk | Post-Plan Risk | Risk Rating Decriptors | Elements and Actions in the RX Fire Plan that Address Risk Mitigation
Safety | Mod | Mod | • Safety issues are pronounced and require detailed briefings, with certain hazards requiring special caution. • A small organization with a single branch results in modest exposure of personnel to hazards. • Adverse impacts to public health and safety are possible. • At least one activity is low frequency/high risk. • Fatigue and extended exposure to hazards are anticipated. | Free Text
Fire Behavior | High | High | • Major variations in the fuel complex are likely to result in more intense fire behavior variations. • Wide variations in fire behavior may present major control challenges. • Terrain encompasses a wide range in slope steepness, abrupt changes in slope, and several directional aspects that lead to widely variable and unpredictable local winds and microclimate differences. • High intensity fire behavior may be expected outside the unit with high rates of spread, torching, possible crown fire runs. • Probability of ignition outside of the unit is high and short and long range spotting can be expected. • Potential fire spread and behavior outside the unit is equal to or greater than inside the unit. | Free Text
Resistance to Containment | Mod | Mod | • Potential for multiple wildfire mechanisms such as spot fires or slopovers that can propagate at moderate rates of spread but can be held by prompt holding actions. • Some fuel concentrations or ladder fuels exist near critical holding points. • Expected fire intensities in the primary fuel type create little potential to challenge standard fire lines. • The probability of ignition in fuels outside of control lines is low to moderate. • Some dependency on natural fuel breaks to hold the prescribed fire. • Local drought and or fire indices are expected to be moderate to high. | Free Text
Ignition Procedures and Methods | Mod | Low | • An unexpected or adverse event is unlikely and coordination of firing sequence, patterns and timing is not critical to meet project objectives. • Specific fire intensities or rate of spread (ROS) are not critical for meeting resource objectives. | Free Text
Prescribed Fire Duration | Mod | Mod | • Active ignition, fire spread, and patrol is expected to occur for several operational periods. • Some residual burning (heavy fuel smoldering, stump holes, etc.) is expected to occur for several days after the primary burn out of the unit. • Mop-up and patrol is typical with minimal resource and equipment needs. • Primary holding phase is expected to be completed within reasonably predictable local weather forecasts. • The prescribed fire depends on accurate forecasts through three days. | Free Text
Free Text
Smoke Management | High | Mod | • Noticeable smoke will be produced creating at least some public concern. • Short-term health or safety concerns related to smoke exposure may occur if actual weather deviates from forecasted. • Nearby communities are highly conscious of smoke from wildland fire. • Some possibility for a NAAQS exceedance violation. • The prescription or ignition portions of the plan need to consider smoke management. | Free Text
Number and Dependence of Activities | Mod | Mod | • Several activities depend on achievement of previous or concurrent actions. • Several activities are interactive. • Communication is routine for coordination of activities and project success. • The project involves another land management agency, ownership or jurisdiction but project completion is not dependent on coordinated implementation. • Adjacent ownership supports the implementation of the prescribed fire. | Free Text
Management Organization | Mod | Mod | • Two levels of supervision are needed (i.e. Burn Boss, Ignition Specialist, and/or Holding Specialist, plus lighters and holders). • Special skills or supervision required for one function (RXB2 is suggested). | Free Text
Free Text
Treatment/Resource Objectives | Mod | Low | • Few if any issues are present that hamper meeting treatment resource objectives. • Few or no adverse impacts are expected if resource objectives are not met. • No critical holding points. | Free Text
Free Text
Constraints | Low | Low | • Constraints exist with little impact on implementing the prescribed fire or achieving objectives. | Free Text
Free Text
Project Logistics | Mod | Mod | • Some phases of the prescribed fire may require logistical support in order to safely meet project objectives. • Limited amount of special equipment or communication equipment requiring more intensive logistical support may be needed to complete the project. | Free Text
Free Text
Note on A2: SAFETY Hazards to personnel and public from planned prescribed fire activities through all phases of the prescribed fire. Safety is always considered individually for all elements.
Note on A4: FIRE BEHAVIOR The difficulty of achieving the desired range of fire intensity, rate of spread and flame lengths to meet the prescribed fire objectives.
Note on A6: RESISTANCE TO CONTAINMENT: The conditions that influence the potential for a prescribed fire to leave the ignition unit or project area and resist containment effort.
Note on A8: IGNITION PROCEDURES AND METHODS Number and type of ignition devices, patterns, sequencing and/or timing required to safely ignite the prescribed fire and meet the objectives.
Note on A10: PRESCRIBED FIRE DURATION The length of time (hours, days or weeks) that active ignition, fire spread, and primary holding operations (critical holding points are secure, transitioning to mop-up and patrol, etc.) are expected to occur in order to fully implement the prescribed fire.
Note on A12: SMOKE MANAGEMENT The actions implemented by prescribed fire personnel directed at reducing the amount of smoke entering populated areas or impacting sensitive sites. Smoke management includes avoiding significant deterioration of air quality and violations of National Ambient Air Quality Standards, and minimizing or eliminating visibility impacts in Class I areas.
Note on A14: NUMBER AND DEPENDENCE OF ACTIVITIES Number and sequence of activities required to safely implement the prescribed fire and meet objectives through all phases of the project, including logistics, pre and post burn considerations, communication, test fire, ignition and holding operations, contingency actions (if implemented), mop-up and patrol, monitoring, and ensuring firefighter and public safety.
Note on A16: MANAGEMENT ORGANIZATION The organizational capabilities needed to safely achieve objectives specified in the prescribed fire plan. This includes all phases of the prescribed fire until declared out.
Note on A18: TREATMENT/ RESOURCE OBJECTIVES The degree of difficulty to meet specific, measurable, achievable, realistic, time-sensitive treatment and resource objectives for the prescribed fire.
Note on A20: CONSTRAINTS Conditions or requirements that place sideboards on the prescribed fire plan implementation. Example: Seasonal timing, logistical restrictions, smoke management restrictions, and national preparedness levels four, and five.
Note on A22: PROJECT LOGISTICS Facilities, services and supplies required to support all phases of the prescribed fire (includes access complexity).

## Post-Plan Technical Difficulty
Element | Post-Plan Risk | Technical Difficulty | Rating Descritors
Safety | Mod | Low | • No special actions are required to mitigate potential minor accidents or injuries identified in the risk assessment/Job Hazard Analysis (JHA). • Safety concerns can be easily mitigated through LCES. • No preparation work or special project design features are required.
Fire Behavior | High | Low | • Standard fire safety precautions are adequate to ensure personnel safety. • No fire behavior variations are expected and numerous barriers to fire spread exist. • The number, size or likelihood of spot fires and slopovers is minimal and do not require additional suppression resources. • Fire behavior is such that holding forces can easily control possible spot fires and slopovers using direct attack tactics. • No on-site operational fire behavior specialists are required.
Resistance to Containment | Mod | Mod | • Several types of resources are involved in the holding operation. • Some portions of the burn unit and project area are not easily accessible to the holding resources. • Expected fire behavior outside the unit may require developing indirect attack options. • Areas outside of the project area have specific suppression action constraints or are on other jurisdictional lands that may limit containment efforts. • Some site prep is required. • Expected fire behavior outside of the unit requires moderate contingency planning.
Ignition Procedures and Methods | Low | Low | • There is no need for special firing equipment, techniques, or patterns. • Firing procedures are simple and ignition team is small. • Use of only one type of ignition device is planned. • The ignition pattern requires minimal supervision of the lighters to achieve project objectives and manage safety concerns. • Communications are easily maintained with a single tactical frequency. • The entire project area is readily visible to the Firing/Burn Boss.
Prescribed Fire Duration | Mod | Low | • Ignition and mop-up operations are usually completed in 1 to 2 operational periods. • Mop-up and patrol is typical with minimal resource and equipment needs. • Standard press release is sufficient for public notification.
Smoke Management | Mod | Mod | • ERTs and SMTs require skilled application of the prescribed fire prescription. • Some considerations are needed in the prescription or ignition portions of the plan to employ ERTs, and SMTs. • Wind parameters are constrained but easy to achieve. • Sensitive receptors exist. • Burn window/opportunities are reduced by the required weather/dispersion conditions. • Normal coordination with air quality officials is required. • Some mitigation measures or additional smoke modeling may be needed to address potential concerns with smoke impacts. • Specific smoke monitoring may be required to determine smoke plume heights and directions. • Rotating project personnel out of dense smoke may be necessary but easy to accomplish. • Daily smoke management forecasts are adequate.
Number and Dependence of Activities | Mod | Mod | • Holding and lighting require close coordination and are dependent on each other to prevent spots or slopovers. • Continuous communication is necessary for successful project completion. • Some pre-burn considerations are required before ignition.
Management Organization | Mod | Low | • All team members are available within the local unit and are familiar with local factors affecting project implementation. • Several qualified personnel are available. • The operation is carried out employing a small burn crew. • There is no special pre-burn preparation organization is required.
Treatment/Resource Objectives | Low | Low | • There are few resource objectives to meet. • Measures to achieve the objectives are easy to complete and there are few or no restrictions on techniques. • There are few or no restrictions on techniques and prescription parameters. • Basic monitoring of fire behavior and weather is needed to determine if prescribed fire objectives are being met. • Many other opportunities will exist to meet objectives in a given year. • Pre-burn site preparation is not required to meet resource objectives.
Constraints | Low | Low | • Constraints are easily accommodated and do not increase the difficulty of completing the project or achieving objectives. • Required weather and fuel conditions are locally very common.
Project Logistics | Mod | Mod | • Project implementation requires a small logistical support operation. • Logistical support may be combined with other functions. • Obtaining some personnel may require additional contacts and advanced scheduling. • Additional support may be needed for out-of-area personnel. • Project duration may require a resupply to ensure successful remote prescribed fire implementation. • Support for meals, sanitation and camping sites may be required to complete the project. • Project is remote with long travel periods.
Note on C1: Technical Difficulty The degree of skill required by prescribed fire personnel and the relative difficulty of implementing mitigation actions identified in the prescribed fire plan
Note on A2: SAFETY Hazards to personnel and public from planned prescribed fire activities through all phases of the prescribed fire. Safety is always considered individually for all elements.
Note on C2: The degree of skill required by prescribed fire personnel and the relative difficulty of implementing mitigation actions identified in the prescribed fire plan that are directed at minimizing hazards to personnel and the public from environmental or prescribed fire activities through all phases of the prescribed fire.
Note on A4: FIRE BEHAVIOR The difficulty of achieving the desired range of fire intensity, rate of spread and flame lengths to meet the prescribed fire objectives.
Note on C4: What degree of skill is required by prescribed fire personnel for predicting, producing, & sustaining the desired range of fire intensity, rate of spread and flame lengths to meet the prescribed fire objectives? What is the difficulty of maintaining containment of the prescribed fire under required fire behaviors to meet objectives? Are there specific skills or equipment needed for special or unusual ignition devises to produce or sustain desired fire behavior(s) i.e terra / heli torch, PSD?
Note on A6: RESISTANCE TO CONTAINMENT: The conditions that influence the potential for a prescribed fire to leave the ignition unit or project area and resist containment effort.
Note on C6: The conditions that influence the potential for a prescribed fire to leave the ignition unit or project area and resist containment efforts.
Note on A8: IGNITION PROCEDURES AND METHODS Number and type of ignition devices, patterns, sequencing and/or timing required to safely ignite the prescribed fire and meet the objectives.
Note on C8: The skill level(s) of the prescribed fire team to adequately manage the number and type of ignition devices, patterns, sequencing and/or timing required to safely ignite the prescribed fire and meet project objectives.
Note on A10: PRESCRIBED FIRE DURATION The length of time (hours, days or weeks) that active ignition, fire spread, and primary holding operations (critical holding points are secure, transitioning to mop-up and patrol, etc.) are expected to occur in order to fully implement the prescribed fire.
Note on C10: The length of time (hours, days or weeks) that active ignition, fire spread and primary holding operations (critical holding points are secure, transitioning to mop-up and patrol etc.) are expected to occur in order to fully implement the prescribed fire.
Note on A12: SMOKE MANAGEMENT The actions implemented by prescribed fire personnel directed at reducing the amount of smoke entering populated areas or impacting sensitive sites. Smoke management includes avoiding significant deterioration of air quality and violations of National Ambient Air Quality Standards, and minimizing or eliminating visibility impacts in Class I areas.
Note on C12: The degree of skill required by prescribed fire personnel and the relative difficulty of implementing the prescribed fire plan actions directed at minimizing the amount of smoke entering populated areas or impacting sensitive sites, avoiding significant deterioration of air quality and violations of National Ambient Air Quality Standards, and mitigating human-caused visibility impacts in Class I areas.
Note on A14: NUMBER AND DEPENDENCE OF ACTIVITIES Number and sequence of activities required to safely implement the prescribed fire and meet objectives through all phases of the project, including logistics, pre and post burn considerations, communication, test fire, ignition and holding operations, contingency actions (if implemented), mop-up and patrol, monitoring, and ensuring firefighter and public safety.
Note on C14: The degree of skill required and the relative difficulty of implementing actions directed at managing and coordinating the number and sequence of activities required to safely implement the prescribed fire and meet objectives through all phases of the project. This includes logistics, pre and post burn considerations, communication, test fire, ignition and holding operations, contingency actions (if implemented), mop-up and patrol, monitoring, and ensuring firefighter and public safety.
Note on A16: MANAGEMENT ORGANIZATION The organizational capabilities needed to safely achieve objectives specified in the prescribed fire plan. This includes all phases of the prescribed fire until declared out.
Note on C16: What are organizational capabilities needed to safely achieve objectives specified in the prescribed fire plan. This includes all phases of the prescribed fire until declared out.
Note on A18: TREATMENT/ RESOURCE OBJECTIVES The degree of difficulty to meet specific, measurable, achievable, realistic, time-sensitive treatment and resource objectives for the prescribed fire.
Note on C18: The degree of difficulty to meet specific, measurable, achievable, realistic, time-sensitive (s.m.a.r.t) resource objectives. (How big is the just right window?)
Note on A20: CONSTRAINTS Conditions or requirements that place sideboards on the prescribed fire plan implementation. Example: Seasonal timing, logistical restrictions, smoke management restrictions, and national preparedness levels four, and five.
Note on C20: Assesses the level of skills required to adequately plan for and safely execute the prescribed fire within identified constraints while still achieving desired objectives
Note on A22: PROJECT LOGISTICS Facilities, services and supplies required to support all phases of the prescribed fire (includes access complexity).
Note on C22: The difficulty and skill required to obtain all required facilities, services and supplies to support all phases of the prescribed fire (includes access into and out of project area.)

## Summary and Final Complexity
Type the Prescribed Fire Plan name here |  | Quantity | Significance
Values | On-Site | None | Low
| Off-Site | Multiple | Mod
| Public/Political Interest | Few | High
| Element | Preliminary Risk | Post-Plan Risk | Technical Difficulty | Calculated Rating
| Safety | Mod | Mod | Low | Mod
| Fire Behavior | High | High | Low | High
| Resistance to Containment | Mod | Mod | Mod | Mod
| Ignition Procedures and Methods | Mod | Low | Low | Low
| Prescribed Fire Duration | Mod | Mod | Low | Mod
| Smoke Management | High | Mod | Mod | Mod
| Number and Dependence of Activities | Mod | Mod | Mod | Mod
| Management Organization | Mod | Mod | Low | Mod
| Treatment/Resource Objectives | Mod | Low | Low | Low
| Constraints | Low | Low | Low | Low
| Project Logistics | Mod | Mod | Mod | Mod
| Final Complexity Determination | Final Complexity Determination Rationale
| Mod | This is a free-flow text box. This is where the prescribed fire plan preparor and Agency Administrator document the rationale for determining the prescribed fire complexity. The rationale will clearly justify the rating for the prescribed fire. At a minimum, complexity analysis elements rated high that cannot be mitigated in the prescribed fire plan must be discussed.
Signatures
|  | Rx Burn Plan Preparer's Name:________________________________ |  |  | X____________________________________ | Date:_____________
Preparer
|  | Technical Reviewer's Name:_______________________ |  |  | X___________________________________ | Date:_____________
Technical Reviewer
|  | Agency Administrator's Name:________________________________ |  |  | X___________________________________ | Date:_____________
Agency Administrator
NWCG Prescribed Fire Summary and Final Complexity Worksheet, PMS 424-1
This worksheet is supplemental to the Prescribed Fire Complexity Rating System Guide, PMS 424. It is designed to enable effective risk management. The Interagency Prescribed Fire Planning and Implementation Procedures Guide, PMS 484, provides further explanation. This becomes Element 3 of the Prescribed Fire Plan.
Note on F14: Calculated based on Risk Rating and Technical Difficulty

## Numerical (hidden)
|  | Pre | Post | TechDiff | TotalRating | PreRating
Values | On-Site | 0
| Off-Site | 3
| Public/Political | 2
| Total | 5
| Safety | 2 | 2 | 1 | 2 | 2
Operational | Fire Behavior | 3 | 3 | 1 | 3 | 3
| Resistance to Contain | 2 | 2 | 2 | 2 | 2
| Ignition Procedures | 2 | 1 | 1 | 1 | 2
| Duration | 2 | 2 | 1 | 2 | 2
| Smoke | 3 | 2 | 2 | 2 | 3
Organizational | Dependent Activities | 2 | 2 | 2 | 2 | 2
| Management Organization | 2 | 2 | 1 | 2 | 2
| Management Objectives | 2 | 1 | 1 | 1 | 2
| Constraints | 1 | 1 | 1 | 1 | 1
| Logistics | 2 | 2 | 2 | 2 | 2
Total
| Operational Total | 14 | 12 | 8 | 12 | 14
| Organizational Total | 9 | 8 | 7 | 8 | 9
| Total | 23 | 20 | 15 | 20 | 23
For Graph
[7 empty] | 11 | 1 | Low
[7 empty] | 33 | 1 | High
[7 empty] | 20 | 1 | Total
Note on C7: SAFETY Hazards to personnel and public from planned prescribed fire activities through all phases of the prescribed fire. Safety is also individually considered for all elements (lessons learned bubbles etc…)
Note on C8: FIRE BEHAVIOR The difficulty of achieving the desired range of fire intensity, rate of spread and flame lengths to meet the prescribed fire objectives.
Note on C9: RESISTANCE TO CONTAINMENT: The conditions that influence the potential for a prescribed fire to leave the ignition unit or project area and resist containment efforts.
Note on C10: IGNITION PROCEDURES/METHODS Number and type of ignition devices, patterns, sequencing and timing required to safely ignite the prescribed fire.
Note on C11: PROJECT DURATION The length of time (hours, days or weeks) that active ignition operations, burn out and/or primary holding operations are expected to occur in order to fully implement the treatment.
Note on C12: SMOKE MANAGEMENT The actions implemented by prescribed fire personnel directed at minimizing the amount of smoke entering populated areas or impacting sensitive sites. , avoiding significant deterioration of air quality and violations of National Ambient Air Quality Standards, and mitigating human-caused visibility impacts in Class I areas. (NWCG Glossary).

## List (hidden)
| None | None | 0 |  |  | Final
Low | Nominal | Trivial | 1 | 1 | Low | Low | Yes
Mod | Few | Ordinary | 2 | 2 | Mod | Moderate | No
High | Multiple | Complex | 3 | 3 | High | High
| Considerable | Extraordinary | 4
Values |  |  | TD
Smoke | Low | • Smoke concerns are generally few or easily mitigated. • Smoke will be short-lived or inconspicuous. • Exposure to smoke by firefighters and the public will be minimal. • Few concerns exist about smoke from nearby communities. | • ERTs and SMTs are simple, routine and straightforward to achieve and will provide desirable smoke management outcomes. • Some limitations may be present in the plan. • Wind and dispersion parameters are not constrained. • No sensitive receptors exist. • Minimal coordination with air quality officials is required.
| Mod | • Noticeable smoke will be produced creating at least some public concern. • Short-term health or safety concerns related to smoke exposure may occur if actual weather deviates from forecasted. • Nearby communities are highly conscious of smoke from wildland fire. • Some possibility for a NAAQS exceedance violation. • The prescription or ignition portions of the plan need to consider smoke management. | • ERTs and SMTs require skilled application of the prescribed fire prescription. • Some considerations are needed in the prescription or ignition portions of the plan to employ ERTs, and SMTs. • Wind parameters are constrained but easy to achieve. • Sensitive receptors exist. • Burn window/opportunities are reduced by the required weather/dispersion conditions. • Normal coordination with air quality officials is required. • Some mitigation measures or additional smoke modeling may be needed to address potential concerns with smoke impacts. • Specific smoke monitoring may be required to determine smoke plume heights and directions. • Rotating project personnel out of dense smoke may be necessary but easy to accomplish. • Daily smoke management forecasts are adequate.
| High | • Conspicuous smoke will be produced creating significant public concern. • The possibility of health and safety issues due to smoke exposure exists. • Strong, widespread social/political concern about smoke is common in the affected area. • High possibility for a NAAQS exceedance violation. • Smoke impacts affect several prescribed fire plan elements. | • Several considerations are needed in the prescribed fire plan in order to balance ERTs and SMTs against prescribed fire objectives. • Must be implemented under multiple specific constraints (specific wind parameters, season, etc.) to prevent impacts to sensitive smoke receptors. • Burn window/opportunities are limited by the required weather/dispersion conditions. • Special coordination with air quality officials is required. • Accelerated mop-up may be planned to reduce smoke impacts. • Some mitigation measures or additional smoke modeling are required to address potential concerns with smoke impacts. • Specific smoke monitoring is required to determine smoke plume heights and directions. . • Forecasts of long term atmospheric stability are required due to duration of the prescribed fire burn.
Fire Behavior | Low | • Terrain is mostly flat or the slope and aspect are uniform, leading to a relatively unvarying fire. • Winds, fuel moisture, microclimate, and other fire conditions are relatively uniform and are not conducive to active fire spread. • Fire behavior is highly predictable. • Fire spread beyond the immediate ignition area(s) is not likely to occur or contribute to any control problems. | • Standard fire safety precautions are adequate to ensure personnel safety. • No fire behavior variations are expected and numerous barriers to fire spread exist. • The number, size or likelihood of spot fires and slopovers is minimal and do not require additional suppression resources. • Fire behavior is such that holding forces can easily control possible spot fires and slopovers using direct attack tactics. • No on-site operational fire behavior specialists are required.
| Mod | • Fuels vary within the unit, both in loading and arrangement. • Fire behavior may present control challenges that are easily mitigated. • Medium fuel loadings with some high concentrations are present. • Variable terrain features may significantly affect fire behavior and present moderate ignition and control problems. • Local winds and burning conditions may vary enough to cause shifts in fire behavior that briefly exceed modeled fire behavior and threaten controllability. • Periodic torching can be expected either as isolated points or in limited areas. • Probability of ignition outside of the unit is low and any spotting is expected to be short-range. | • Some special provisions for safety are needed to protect personnel. • Fire behavior variations are minimal and do not require multiple fuel models to account for the fire behavior. • At least one barrier or containment opportunity exists. • Fire behavior is such that holding resources may need to use indirect tactics to control some spot fires and slopovers. • Occasional on-site fire behavior assessments or calculations may be needed and can be performed as a collateral duty. • Emission Reduction Techniques (ERTs) and Smoke Management Techniques (SMTs) require a close adherence to the prescription in the Rx plan.
| High | • Major variations in the fuel complex are likely to result in more intense fire behavior variations. • Wide variations in fire behavior may present major control challenges. • Terrain encompasses a wide range in slope steepness, abrupt changes in slope, and several directional aspects that lead to widely variable and unpredictable local winds and microclimate differences. • High intensity fire behavior may be expected outside the unit with high rates of spread, torching, possible crown fire runs. • Probability of ignition outside of the unit is high and short and long range spotting can be expected. • Potential fire spread and behavior outside the unit is equal to or greater than inside the unit. | • Fire behavior may create unique safety problems or the need for special escape routes or other safety measures. • Fire behavior variations require the use of several fuel models to develop the prescription parameters. • Limited containment opportunities exist. • Fire behavior is such that additional holding resources would be required along with indirect attack tactics. • Systematic fire behavior assessments and calculations are needed by a dedicated skill position. • Fire Behavior Analyst (FBAN) or Long Term Analyst (LTAN) is suggested for short or long duration prescribed fire operations, respectively. • ERTs and SMTs require a strict adherence to the prescription in the Rx plan the extensive contingency planning.
Ignition Procedures | Low | • An unexpected or adverse event is unlikely and coordination of firing sequence, patterns and timing is not critical to meet project objectives. • Specific fire intensities or rate of spread (ROS) are not critical for meeting resource objectives. | • There is no need for special firing equipment, techniques, or patterns. • Firing procedures are simple and ignition team is small. • Use of only one type of ignition device is planned. • The ignition pattern requires minimal supervision of the lighters to achieve project objectives and manage safety concerns. • Communications are easily maintained with a single tactical frequency. • The entire project area is readily visible to the Firing/Burn Boss.
| Mod | • Multiple firing sequences patterns and timing must be coordinated to meet project objectives and reduce the risk of an unexpected or adverse event. • Specific fire intensities or ROS are somewhat critical for meeting resource objectives but are readily attained by placing local skill sets in firing boss positions. | • The need for multiple firing devices, sequences, techniques, or patterns has been identified. • Firing procedures are somewhat complex in at least some portions of the project area and a single Firing Boss (FIRB) is used. • Two different types of ignition devices are planned. • The ignition pattern requires direct control of the lighters to achieve project objectives and manage safety concerns. • Communications may require the use of a command (repeater) and at least two tactical frequencies will be used. • The project area is large but can be observed from high points and terrain and/or distance does not contribute to sequence and timing problems.
| High | • Multiple firing devices, firing sequences, patterns, coordination and timing are critical to meet project objectives and reduce the risk of an unexpected adverse event. • Specific fire intensities or ROS are critical for meeting resource objectives. The use of experienced skill sets in supervision and lighting is mandatory for meeting objectives. | • The need for multiple special firing equipment or different techniques or firing sequences or patterns has been identified. • Firing procedures are complex and the ignition function may be broken into multiple teams with more than one FIRB is used. • Simultaneous ignitions will occur that require precise timing and communications to insure safety. • Ignition patterns and techniques to manipulate fire behavior are used and require tight control of the lighters to achieve project objectives and manage safety concerns. • Specialized communication equipment and planning (Portable or human repeater) is necessary to direct ignition operations. • More than three tactical frequencies will be used. • Many portions of the project area are not readily visible to the Firing Boss and Burn Boss.
Duration | Low | • Ignition operations should be accomplished within one operational period. • Burn unit is small in size and residual burning is not expected after primary burn out of the unit. • Decrease in seasonal severity is expected. • Short time frame does not require special logistical support. • Mop-up is minimal or none is anticipated/planned. | • Ignition and mop-up operations are usually completed in 1 to 2 operational periods. • Mop-up and patrol is typical with minimal resource and equipment needs. • Standard press release is sufficient for public notification.
| Mod | • Active ignition, fire spread, and patrol is expected to occur for several operational periods. • Some residual burning (heavy fuel smoldering, stump holes, etc.) is expected to occur for several days after the primary burn out of the unit. • Mop-up and patrol is typical with minimal resource and equipment needs. • Primary holding phase is expected to be completed within reasonably predictable local weather forecasts. • The prescribed fire depends on accurate forecasts through three days. | • Ignition and mop-up operations are usually completed within 3 - 7 operational periods. • Multiple shifts may need staffing (day/night). • Required staffing may affect resource availability for other prescribed fires. • Additional dispatch support may be required. • Standard press release is sufficient for public notification. • The units Public Affairs Office (PAO) is required to be available to field questions from media and public. • Some fire behavior assessment is necessary to identify potential seasonality fire behavior. • Only a few Management action points (MAPs) are needed to identify how the fire will be managed if unfavorable events occur. • The length of time to complete the project and the size of the organization needed may increase. • ERTs and SMTs require daily attention to ensure that smoke constraints are not exceeded.
| High | • Long-term active ignition operations or fire spread is required to meet prescribed fire objectives. • A large amount of residual burning (heavy fuel smoldering, stump holes, etc.) or residual burning over a large area is expected to occur for at least a week after the primary ignition of the unit. • Long term mop-up and patrol with multiple resource types and equipment. • Primary holding phase may exceed reasonably accurate weather predictions. • Prescribed fire depends on accurate weather forecasts beyond over a three-day period. | • Ignition, mop-up and patrol operations will last longer than 7 days, potentially for weeks. • Management organization will have to be adjusted to account for fire activity. • Multiple resource types and equipment. • Systematic fire behavior assessments and calculations are needed by a dedicated skill position (SOPL, FBAN or LTAN). • Additional dispatch support will be required. • A dedicated PAO will be on-site to field questions from media and public. • MAPs are required that will address how the fire will be managed if unfavorable events occur. • The length of time to complete the project and the size of organization will increase as season progresses. • Close coordination with States Department of Environmental Quality will be needed to ensure that short and long term smoke outputs can be managed and constraints are not exceeded.
Resistance to Containment | Low | • Ranges from no potential to a likelihood of few mechanisms such as spot fires, slopovers or fire creeping, each comprising small areas that are readily detected, accessed, and controlled by holding resources available on the prescribed fire. • No ladder fuels or concentrations are near critical holding points. • Ignition procedures do not create intense fire behavior. • Probability of ignition in fuels outside the unit is low. • Local drought and or fire danger indices are expected to be low to moderate. | • Minimal holding resources are involved in the holding operation. • The burn unit and project area is easily accessible to the holding resources identified in the plan. • Minimal line width required to contain expected fire spread. • Minimal site prep is required.
| Mod | • Potential for multiple wildfire mechanisms such as spot fires or slopovers that can propagate at moderate rates of spread but can be held by prompt holding actions. • Some fuel concentrations or ladder fuels exist near critical holding points. • Expected fire intensities in the primary fuel type create little potential to challenge standard fire lines. • The probability of ignition in fuels outside of control lines is low to moderate. • Some dependency on natural fuel breaks to hold the prescribed fire. • Local drought and or fire indices are expected to be moderate to high. | • Several types of resources are involved in the holding operation. • Some portions of the burn unit and project area are not easily accessible to the holding resources. • Expected fire behavior outside the unit may require developing indirect attack options. • Areas outside of the project area have specific suppression action constraints or are on other jurisdictional lands that may limit containment efforts. • Some site prep is required. • Expected fire behavior outside of the unit requires moderate contingency planning.
| High | • There is a potential for multiple wildfire mechanisms (spot fires, slopovers, fire creeping etc.) that exceeds the capability of the holding force to detect and suppress. • Fuel concentrations near critical holding points include ladder fuels that challenge holding operations. • Expected fire intensities in the primary fuel type creates potential to challenge standard fire lines. • Probability of ignition in fuels outside the unit is moderate to high. • High dependence on natural fuel breaks to hold the prescribed fire. • Local drought and or fire indices are expected to be high to extreme. | • Many types of resources are involved in the holding operation. • Several portions of the burn unit and project area are not easily accessible and or some portions are inaccessible to the holding resources. • Expected fire behavior outside the unit requires development of indirect attack plans. • If the prescribed fire leaves the burn unit boundary it will enter a highly restrictive suppression resource area such as wilderness, swamp, unexploded ordinances (UXOs), cultural site that will directly impact on-site holding resource ability to contain the fire. • Extensive site preparation is required. • Expected fire behavior outside of the unit requires extensive contingency planning.
Dependent Activities | Low | • Activities are mostly independent from each other. • Coordination of activities is simple and straightforward. • The project does not involve another land management agency or jurisdiction. | • Minimal difficulty in coordinating the required activities. • Holding and lighting are loosely dependent on each other. • Coordination problems or communication failures or issues will not affect the completion of the project. • No to very few pre-burn considerations are required.
| Mod | • Several activities depend on achievement of previous or concurrent actions. • Several activities are interactive. • Communication is routine for coordination of activities and project success. • The project involves another land management agency, ownership or jurisdiction but project completion is not dependent on coordinated implementation. • Adjacent ownership supports the implementation of the prescribed fire. | • Holding and lighting require close coordination and are dependent on each other to prevent spots or slopovers. • Continuous communication is necessary for successful project completion. • Some pre-burn considerations are required before ignition.
| High | • Numerous highly interactive activities are required for project success. • Numerous activities are complex and highly interactive. • High degree of coordination is required to manage prescribed fire implementation. • The project involves other land management agencies or jurisdictions and project completion is dependent on coordinated implementation. • Adjacent lands are excluded due to the lack of support for the prescribed fire treatment. | • Requires a highly skilled team to successfully complete the project. • Continuous coordination and communication is critical to the success of the project. • Requires implementation personnel to be familiar with capabilities of the resources used. • Multiple pre-burn considerations are required to take place before ignition.
Management Organization | Low | • A small number of qualified people are required to implement the prescribed fire. • A single level of supervision is all that is needed (i.e. Burn Boss plus lighters and holders). | • All team members are available within the local unit and are familiar with local factors affecting project implementation. • Several qualified personnel are available. • The operation is carried out employing a small burn crew. • There is no special pre-burn preparation organization is required.
| Mod | • Two levels of supervision are needed (i.e. Burn Boss, Ignition Specialist, and/or Holding Specialist, plus lighters and holders). • Special skills or supervision required for one function (RXB2 is suggested). | • At least one primary team member may need to come from outside of the local unit and may not be familiar with local factors. • The numbers of qualified personnel available on the local unit are limited. • Special skills or supervision required for one function (RXB2 suggested). • Some pre-burn preparation work may require special organizational planning and/or coordination. • Protection of resource values requires extra considerations when developing certain elements of the prescribed fire plan. • Few resources are required for mop-up and patrol.
| High | • Three levels of supervision may be needed (i.e. Burn Boss, FIRB, Holding Function, plus Squad Leaders and Squads) or multiple teams are needed to cover multiple shifts or a long duration project. • Special skills or supervision required for more than one function (RXB1 suggested). • Large organization increases potential for safety issues. • Considerable pre-burn preparation work is required. | • Numerous and varied resources require a large team of specialized positions. • The prescribed fire has difficult access, complicated logistics, potentially conflicting objectives, unusual fuel complexes, and is proximate to smoke sensitive/non-attainment areas or wildland urban interface, and/or large scale/long duration. • The Burn Boss and/or two or more primary team members may need to be ordered from outside the local unit and may not be familiar with local factors. • Certain skills and qualified personnel are not available on the local unit. • Protection of values requires the development of special ignition AND holding plans. • Special skills or supervision required for more than one function. An RXB1 is suggested. • Numerous resources required for mop-up and patrol.
Treatment Objectives | Low | • Few if any issues are present that hamper meeting treatment resource objectives. • Few or no adverse impacts are expected if resource objectives are not met. • No critical holding points. | • There are few resource objectives to meet. • Measures to achieve the objectives are easy to complete and there are few or no restrictions on techniques. • There are few or no restrictions on techniques and prescription parameters. • Basic monitoring of fire behavior and weather is needed to determine if prescribed fire objectives are being met. • Many other opportunities will exist to meet objectives in a given year. • Pre-burn site preparation is not required to meet resource objectives.
| Mod | • Issues are present that hamper or may prevent meeting treatment resource objectives. • Failure to meet objectives could have short-term adverse impacts. • Associated resources could be damaged if the prescribed fire did not meet resource objectives. • Few critical holding points. | • There are several resource objectives to meet. • Measures to achieve the objectives are either 1) easy to complete but there are restrictions on the techniques or 2) moderately difficult to complete and there are few or no restrictions on techniques. • Additional monitoring of fire behavior and weather is needed to determine if prescribed fire objectives are being met. • Other opportunities to meet objectives are very limited in a given year.
| High | • Substantial issues are present that hamper or prevent meeting treatment resource objectives. • Failure to meet objectives may have adverse long term impacts to resources. • Associated resources would be damaged if the prescribed fire did not meet resource objectives. • High intensity fire behavior is required in the unit to meet objectives. • Many critical holding points and considerable pre-burn preparation work is required to meet resource objectives. | • There are a high number of resource objectives. • Measures to achieve the objectives are both moderately difficult to highly difficult to achieve and there are restrictions on the techniques. • Extensive monitoring of fire behavior and weather is needed to determine if prescribed fire objectives are being met. • Opportunities to meet objectives are not available every year or may not be achievable without extensive fuels preparation work. • Objectives include changes in several strata of vegetation for ecosystem restoration or hazardous fuels reduction.
Constraints | Low | • Constraints exist with little impact on implementing the prescribed fire or achieving objectives. | • Constraints are easily accommodated and do not increase the difficulty of completing the project or achieving objectives. • Required weather and fuel conditions are locally very common.
| Mod | • Constraints exist with some constraints imposing limits on implementing the prescribed fire or achieving objectives. | • Some constraints are not easily accommodated and increase the difficulty of completing the project or achieving objectives. • Some prescribed fire parameters are dependent upon marginal environmental conditions. • The length of time to complete the project and the size of the organization may need to be increased.
| High | • Significant and/or competing constraints exist and impose limits on implementing the prescribed fire or achieving objectives. | • Constraints are hard to accommodate and significantly increase the difficulty of completing the project or achieving objectives. • Windows of opportunity or conditions within prescribed parameters rarely occur in the project area. • The length of time to complete the project and the size of organization will need to be increased and project feasibility may be in doubt.
Logistics | Low | • Minimal logistical support is needed to safely meet prescribed fire objectives. • No special equipment, support or communications needs are required. | • No specific logistic function is required and the local unit will handle their own support needs. • Project is nearby and easily accessible. • Local cache can supply the needs of the prescribed fire.
| Mod | • Some phases of the prescribed fire may require logistical support in order to safely meet project objectives. • Limited amount of special equipment or communication equipment requiring more intensive logistical support may be needed to complete the project. | • Project implementation requires a small logistical support operation. • Logistical support may be combined with other functions. • Obtaining some personnel may require additional contacts and advanced scheduling. • Additional support may be needed for out-of-area personnel. • Project duration may require a resupply to ensure successful remote prescribed fire implementation. • Support for meals, sanitation and camping sites may be required to complete the project. • Project is remote with long travel periods.
| High | • Extensive dedicated logistical support through most phases of the prescribed fire is required to safely meet project objectives. • Large amount of equipment or a communications network is needed that require intensive logistical support. | • Project implementation requires a large logistical support operation. • Separate logistical functions or a logistics team is required. • Obtaining the necessary personnel requires at least some additional contacts and does require careful scheduling. • Additional support will be needed for out-of-area personnel. • Scarce supplies/equipment requires extra lead-time to procure. • Support of meals, sanitation and camping sites are required in order to objectives. • Remote locations difficult to access or inaccessible to vehicles.
Safety | Low | • Safety issues and hazards are easily identifiable, addressed in briefings, and managed. • Minimal organization produces little exposure of personnel to hazards. • Adverse impacts to public health and safety are unlikely. • Activities are high frequency/low risk. • Fatigue and exposure to hazards are limited. • Standard safety briefings and attention to Lookouts, Communications, Escape Routes, and Safety Zones (LCES) are sufficient. | • No special actions are required to mitigate potential minor accidents or injuries identified in the risk assessment/Job Hazard Analysis (JHA). • Safety concerns can be easily mitigated through LCES. • No preparation work or special project design features are required.
| Mod | • Safety issues are pronounced and require detailed briefings, with certain hazards requiring special caution. • A small organization with a single branch results in modest exposure of personnel to hazards. • Adverse impacts to public health and safety are possible. • At least one activity is low frequency/high risk. • Fatigue and extended exposure to hazards are anticipated. | • Potential serious accidents/injuries or multiple accidents/injuries to personnel or public are mitigated by standard safety briefings and identified in existing risk assessments/JHA. • Special emphasis is needed for some elements of LCES. Some standard preparation work and/or project design features are required.
| High | • Complex safety issues and significant hazards exist that require special briefings and cautions. • A large organization with multiple branches results in an increase of hazard exposure to personnel. • Adverse impacts to public health and safety are likely without appropriate mitigation. • Several activities are low frequency/high risk. • Fatigue and prolonged exposure to hazards require major consideration and specific mitigation. | • Potential for serious accidents/injuries or multiple accidents/injuries to personnel or public have to be addressed with specific safety briefings. • Unusual number of JHAs or risk assessment elements is required to be analyzed. • A new risk assessment or JHA is required to be developed. • Careful attention to all elements of LCES is required. • Special or unique mitigation efforts are required. • A Safety Officer is recommended.
Note on A11: FIRE BEHAVIOR The difficulty of achieving the desired range of fire intensity, rate of spread and flame lengths to meet the prescribed fire objectives.