24 Hour Operational Period Planning Cycle

Day Operational Period (0600-2000)  	Night Operational Period (1800-0800)

Operational Period Schedule (0600 – 2200)

0600	Day Operational Briefing (0600 – 1800)

0900  	DIVS/SITL debrief the Night Shift

0900	Tactics Meeting (ICS-215, for Night Operational Period)

0930 	Deliberate Risk Assessment

1000	Evening Planning Meeting (For Night Operational Period)

1000	MAP updates to SITL

1030 	Agency Administrators Meeting

1100	Cooperators/Stakeholders Meeting

1200	Team Meeting (C&G)

1400	IAP Elements to Plans (for Night IAP)

1500    RESL Provides Corrected 204s to Planning Ops

1730  	Tactic Meeting (ICS-215, for next Day Operational Period)

1800	Night Operational Briefing (1800 – 0600)

1900	Planning Meeting (for next Day Operational Period)

1900	Map updates to SITL (Next Day Operational Period)

2200	DIVS/SITL debrief the Day Shift

2030	IAP Elements to Plans (Next Day Operational Period)

2200	IAP Copying begins

12 Hour Operational Period Planning Cycle

Operational Period (0600-2000)

0600		Operational Briefing

0730		1Cooperators Stakeholders Meeting

0830		1Agency Administrators Meeting

0930 	Deliberate Risk Assessment

1200		Team Meeting (C&G Staff Only)

1700   	Tactic Meeting

1730		Pre-Planning Meeting

1800		Planning Meeting

1900		Map updates to SITL

1900		IAP Elements to Plans

2000		IAP Copying begins

1These meetings will run back-to-back and not necessarily at the start time listed.  They will be scheduled as needed.