INCIDENT TRANSITION PLAN

TEMPLATE

RMA IMT2 Blue

IMT2 Blue is encouraged to utilize this sample template when transitioning to another IMT. It can also be utilized to transition management back to the local unit.  The intent is to provide the needed information to allow as successful and smooth a transition as possible. This is not a narrative document, rather a transfer of critical information to the incoming IMT/Home Unit needed to continue to manage the incident.

IMT Blue should prepare a draft transition plan, utilizing this template, and obtain local agency administrator concurrence at least 24 hours prior to the incoming IMT arrival. They are encouraged to email and/or FAX the draft to the incoming Incident Commander or appropriate C&G staff for advance information.

Not all parts of this Sample Template need be utilized; other important information deemed appropriate for a successful transfer of command should be included. IMT’s are encouraged to utilize existing resource/personnel databases, when available, to minimize duplication of effort.

Additional suggestions:

- Remember this is a PUBLIC DOCUMENT when you prepare it. Be aware that all audiences can and may read what you put in print. Keep comments and observations objective and constructive.

- Involvement of appropriate agency administrators (and Area Commanders), while new, is an important change in transfer of command procedures.

- Do not change font size and style. Font style is Times New Roman and font size is 12 in the body of the plan

- Delete this first page after reading.

- Fill out tables at the end of the documents for those resources remaining on the incident after IMT Blue Demobs.

- Consider how the information you provide to the incoming IMT meets stated Incident Objectives.

INCIDENT NAME:

INCIDENT NUMBER:

Rocky Mountain IMT 2 Blue

to

Team Name Type X Incident Management Team

This Transition Plan will guide the orderly transfer of command on this incident. This Plan, along with the Incident Command System (ICS) Incident Status Summary (ICS 209), applicable maps, resource and demobilization information, and authorizing delegation(s) of authority, adequately summarize the status of the incident sufficient for transfer of command.

An enclosed Complexity Analysis/Organizational Assessment (Section G) documents the decision for the type (level) of incident management team that will assume command.

Plan Approval(s): (required)

| Outgoing Incident Management Team |  |  |
| --- | --- | --- |
| Incident Commander: | Signature: | Date: |

# INCIDENT OBJECTIVES

(State the incident objectives from the latest Form ICS-202, Incident Objectives).

# TRANSITION SCHEDULE and COORDINATION

(Name) Incident Management Team (IMT) will transition with (Name) IMT on (date) and will participate in incident management operations until (name) Team assumes command of the incident at (time) on (date).

(Name) IMT will develop and produce the Incident Action Plan for the (Operational Period). (Name) IMT and (Name) IMT will jointly develop and produce the Incident Action Plan for the (Operational Period). (Name) IMT and (name) IMT will jointly conduct the morning briefing on (date or day) at (location).

# ORGANIZATIONAL NEEDS

A partial list of resources to be left with the incoming IMT, by ICS function, is included in Section E of this narrative. The incoming team should continue to coordinate with (Name of Area Command) in (location) and Expanded Dispatch in (location) regarding the release and reassignment of resources. Area Command or NIMO is primarily interested only in critical resources such as Type 1 crews, aircraft, or others as listed. Critical resources are identified by Area Command or NIMO daily and included in their daily fire summary information.

# FUNCTIONAL HIGHLIGHTS

## Command

State relevant information necessary for the incoming incident commander to understand and successfully function upon transfer of command. Items to consider include the following:

- Political considerations

- Agency Administrator, NIMO, or Area Command expectations

- Documentation/scheduling of FAST, ASTAT, Cost, HR and other oversight teams

- Cost containment objectives and opportunities

- Cooperator involvement

- Various agency objectives

- Daily conference calls

- Community meeting schedules

## Safety

State relevant information necessary for the incoming Safety Officer to understand and successfully function upon transfer of command. Items to consider include the following:

- Major safety hazards (line, camps, transportation, and other)

- Recommended future staffing

- Ongoing investigations and/or reviews

- OSHA relationships

- Evacuations and contingencies

- Fatigue management issues

- Non-operations risk assessments and mitigations employed

- Safety summary including causal factors and mitigation measures employed.

- Daily conference calls

### Medical Unit

- Facility locations

- EMT status in camp

- Summary of personnel injuries and treatments

## Information

State relevant information necessary for the incoming Information Officer to understand and successfully function upon transfer of command. Items to consider include the following:

- Recommended future staffing of Information Function

- Information center locations

- Key talking points, past, present, and future

- Recommended tasks

- Political considerations

- Relationships with local agencies and news outlets (print and electronic)

- Trends

- Daily conference calls

## Liaison

State relevant information necessary for the incoming IMT to understand and successfully function upon transfer of command. Items to consider include the following:

- Staffing, by agency, of Agency Representatives

- Major issues expressed by Agency Representatives, by agency

- Opportunities for improved relations

## Operations

State relevant information necessary for the incoming Operations Section personnel to understand and successfully function upon transfer of command. Items to consider include the following:

- Current strategy and the anticipated probability of success

- Tactical successes

- Tactical barriers

- Cooperator responsibilities, accomplishments to date, and future needs

- Specialized equipment on-scene and needs for the future

- Safety risk assessments and operational mitigations

- Cost containment opportunities

- Supervisory recommendations during transition

- Coordinating needs with adjoining zones or incidents

### Air Operations

- Recommended future staffing for Aviation Branch

- Aviation facility locations (past, present, and future) and capabilities including current issues and future use opportunities. Includes fixed and rotor wing bases, dip sites, re-load bases, portable retardant plants, FAA towers, etc.

- Utilization of current assigned fleet

- Past and existing Temporary Flight Restrictions including number(s)

- Safety risk assessments and operational mitigations

- Operational successes and issues

- Working relationships with cooperators including states and the military

- Communication frequency management and recommendations

- Special operations missions on-going or planned

- Daily conference calls

## Plans

State relevant information necessary for the incoming Planning Section personnel to understand and successfully function upon transfer of command. Items to consider include the following:

- Currency and status of WFSA or other Agency Administrator strategic direction

- Status of planning cycle successes and barriers

- ICS-209 Reporting arrangements

- Recommended future staffing of Planning Section

- Status of planning facilities including equipment (copiers, etc.)

- Status of incident documentation

- Cooperators involvement in planning meetings

- Resource (Advisor) issues, concerns, and opportunities

- Interagency Resource Representative contacts

- Daily conference calls

### Situation Unit

- Brief description of fuels and fire behavior

- Status of mapping capabilities including GIS

- Status of Fire Weather Meteorologists & equipment

### Resources Unit

- Brief description of data base including currency

### Demobilization Unit

- Current status of Demobilization Plan

- Demobilization issues, concerns and opportunities

### Documentation Unit

- Status of documentation

### Training Specialist

- Status of trainees currently on the incident.

- Recommended staffing of Training Specialist position

### Human Resource Management

- Recommended staffing of HRSP positions

- Critical Incident Stress Management resources

- CONCERN/Union relationships

- Employee concerns/morale

## Logistics

State relevant information necessary for the incoming Logistics Section personnel to understand and successfully function upon transfer of command. Items to consider include the following:

- Current and future facility locations

- Recommended future staffing for Logistics Section

- Successes and barriers in working with expanded dispatch

- Equipment and supply shortages to meet operational objectives

- Communications capabilities and barriers

- Applicable supplemental foods policy

- Daily conference calls

### Facilities

- Issues with current facilities

- Status of camp help arrangements

- Existing land use agreements and needs

- Status of shower, laundry services

- Camp safety issues

### Food Unit

- On-scene caterers and capabilities by location

- Food quality, supply

- Local purchasing and supply opportunities

### Ground Support

- Safety considerations

- Travel times for operations personnel

- Equipment considerations (graders, rentals, buses, carts, etc.)

- Environmental considerations (wash stations, etc.)

- Spike camp considerations

- Access and travel management considerations

### Supply Unit

- Status of resource ordering (reconciliation)

- Ordering processes with expanded dispatch including local purchase procedures

- Shortages/excesses of supplies to meet operational objectives

- Use of caches

- Delivery times

- Supply Unit staffing arrangements (Job Corps, AD’s, etc.)

### Communications

- Issues, concerns, opportunities with existing system(s)

- Status of fire line communications

- Status of camp to town communications including cell phone and hard line

- Status of data lines/satellite

- Status of computers, printers, etc.

### Security

- Major security issues (non-confidential)

- Cooperator responsibilities (highways, roadblocks, evacuations, etc.)

- Contingencies

### Computer Specialist

- Status of computer equipment including computers, switches, printers, and network arrangements that will remain in place for the incoming team.

- Procedures for transferring data from one IMT to another.

## Finance

State relevant information necessary for the incoming Finance Section personnel to understand and successfully function upon transfer of command. Items to consider include the following:

- Status of documentation (Finance Package)

- Commissary arrangements

- Agency Incident Business Advisor(s) assigned

- Land Use agreements in effect or needed

- Daily conference calls

- Status of cost containment efforts and relevant documentation

- Recommended future staffing for Finance Section

### Cost Unit

- Status of cost collection mechanisms and daily reports

### Time Unit

- Summary of equipment and personnel time issues, barriers

- Work/rest issues/documentation

- Equipment and personnel time reconciled with resources unit and Incident Action Plan

### Compensation for Claims

- Outstanding claims and/or Compensation for Injury cases

- Potential claims and mitigation measures to avoid

### Procurement Unit

- Status and location of Buying Team(s)

- Numbers of contract crews and engines

- Status of contract inspectors

# OVERHEAD RESOURCES REMAINING

(The use of I-Suite or other data base reports is encouraged in lieu of completing the following sections)

## Command

## (IC’s, all command staff, Agency Representatives)

| ICS Position | Name (last, first) | Resource Order Number | Location | Planned Demobilization Date |
| --- | --- | --- | --- | --- |

## Operations

| ICS Position | Name (last, first) | Resource Order Number | Location | Planned Demobilization Date |
| --- | --- | --- | --- | --- |

## Air Operations

| ICS Position | Name (last, first) | Resource Order Number | Location | Planned Demobilization Date |
| --- | --- | --- | --- | --- |

### Aircraft:

| Type | Tail Number | Resource Order Number | Location | Planned Demobilization Date |
| --- | --- | --- | --- | --- |

## Plans

| ICS Position | Name (last, first) | Resource Order Number | Location | Planned Demobilization Date |
| --- | --- | --- | --- | --- |

## Finance

| ICS Position | Name (last, first) | Resource Order Number | Location | Planned Demobilization Date |
| --- | --- | --- | --- | --- |

## Logistics Personnel

| ICS Position | Name (last, first) | Resource Order Number | Location | Planned Demobilization Date |
| --- | --- | --- | --- | --- |

## Logistics Equipment

| Equipment Type | Vendor / Name / National Fire Equipment System (NFES) Number | Resource Order Number | Location | Planned Demobilization Date |
| --- | --- | --- | --- | --- |

# CONTACT INFORMATION

A list of important contacts, by ICS function, with phone numbers and/or email addresses.  Include both a contact list for Blue Team members, as well as a contact list of agency personnel, partners, and cooperators.

# COMPLEXITY ANALYSIS/organizational assessment

Attach an appropriate complexity analysis sufficient to meet the agency administrator(s)/area commander’s objectives.