Incident Briefing (ICS 201)

| 1. Incident Name: IAP WORKSHOP NASSAU |  | 2. Incident Number: |  | 3. Date/Time Initiated: Date: 07/12/16 Time: 0830 |
| --- | --- | --- | --- | --- |
| 4. Map/Sketch (include sketch, showing the total area of operations, the incident site/area, impacted and threatened areas, overflight results, trajectories, impacted shorelines, or other graphics depicting situational status and resource assignment): |  |  |  |  |
| 5. Situation Summary and Health and Safety Briefing: |  |  |  |  |
| 6. Prepared by: Name: Bob Panko Position/Title: ICT4 Signature: |  |  |  |  |
| ICS 201, Page 1 |  | Date/Time: 07/11/16-1200 |  |

Incident Briefing (ICS 201)

| 1. Incident Name: IAP WORKSHOP NASSAU |  | 2. Incident Number: |  | 3. Date/Time Initiated: Date: 07/12/16 Time: 0830 |
| --- | --- | --- | --- | --- |
| 7. Current and Planned Objectives: - Describe how the National Incident Management System (NIMS) Command and Management component and the Incident Command System support the management of expanding incidents. - Apply the incident/event management process for supervisors and expanding incidents as prescribed by the Incident Command System (ICS). - Apply the incident management process on a simulated Type 3 incident. - Develop an Incident Action Plan for a simulated incident. |  |  |  |  |
| 8. Current and Planned Actions, Strategies, and Tactics: |  |  |  |  |
| Time: | Actions: |  |  |  |
| 0830 | Introductions and Operational Period Briefing |  |  |  |
| 0900 | Review of Principles and Features of ICS |  |  |  |
|  | Review of the ICS Planning Process |  |  |  |
|  | Review of the Responsibilities & Roles of: Incident Commander, Command Staff, Agency |  |  |  |
|  | Representatives, General Staff |  |  |  |
| 1100 | Practical Exercise Start: Agency Administrator Briefing, Initial Action IC Briefing (ICS 201) |  |  |  |
|  | Concur/Edit Incident Objectives, Initial Strategy and Information Sharing Meeting |  |  |  |
| 1130-1230 | LUNCH |  |  |  |
| 1230-1430 | Holding Tactics Meeting, Prepare for Planning Meeting, Hold Planning Meeting, Prepare & Approve IAP |  |  |  |
| 1500-1600 | Using the prepared IAP, hold an Operational Period Briefing for the incoming resources for the next |  |  |  |
|  | Operational Period. |  |  |  |
| 1600-1630 | After Action Review & Close Out |  |  |  |
| 6. Prepared by: Name: Bob Panko Position/Title: ICT4 Signature: |  |  |  |  |
| ICS 201, Page 2 |  |  | Date/Time: 07/11/16-1200 |  |

Incident Briefing (ICS 201)

| 1. Incident Name: IAP WORKSHOP NASSAU | 2. Incident Number: |  | 3. Date/Time Initiated: Date: 07/12/16 Time: 0830 |  |
| --- | --- | --- | --- | --- |
| 9. Current Organization (fill in additional organization as appropriate): Safety Officer Public Information Officer Agency Reps: Dennis Brady – NCOEM Pat Beckley - NYSOEM Operations Section Chief Planning Section Chief Logistics Section Chief Finance/Administration Section Chief Incident Commander(s) Bob Panko Deputy Incident Commander Frank Messar |  |  |  |
| 6. Prepared by: Name: Bob Panko Position/Title: ICT4 Signature: |  |  |  |
| ICS 201, Page 3 |  | Date/Time: 07/11/16-1200 |  |

Incident Briefing (ICS 201)

| 1. Incident Name: IAP WORKSHOP NASSAU |  | 2. Incident Number: |  |  |  |  | 3. Date/Time Initiated: Date: 07/12/16 Time: 0830 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10. Resource Summary: |  |  |  |  |  |  |  |
| Resource | Resource Identifier | Date/Time Ordered |  | ETA | Arrived | Notes (location/assignment/status) |  |
| Anthony Astacio | NYS Park Police |  |  |  |  | student |  |
| Patrick Beckley | NYSOEM |  |  |  |  | student |  |
| Steven Dubin | RVCFD |  |  |  |  | student |  |
| Dov Horwitz | DHSES |  |  |  |  | student |  |
| Ian Jordan | NYSDEC |  |  |  |  | student |  |
| Gary Lewis | NYSP |  |  |  |  | student |  |
| Robert Mangano | TOWN OF OYSTER BAY |  |  |  |  | student |  |
| Nicole Marks | NYSDHSOEM |  |  |  |  | student |  |
| Sharon Muchnick | NYSDOT |  |  |  |  | student |  |
| Kenneth Ryan | NCTY OEM |  |  |  |  | student |  |
| Gary Ryan | NYSP |  |  |  |  | student |  |
| Leonard Symons | TOWN OF OYSTER BAY |  |  |  |  | student |  |
| Eric Zausner | NCTY OEM |  |  |  |  | student |  |
| 6. Prepared by: Name: Bob Panko Position/Title: ICT4 Signature: |  |  |  |  |  |  |  |  |
| ICS 201, Page 4 |  |  | Date/Time: 07/11/16-1200 |  |  |  |  |  |